## Sheet1
| week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | week 12 | week 13 | week 14 | week 15 | week 16 | week 17 | week 18 | week 19 | week 20 | week 21 | week 22 | week 23 | week 24 | week 25 | week 26 | week 27 | week 28 | week 29 | week 30
1.Project initiation | bar: week 1
1.1 Finding a client | bar: week 1
1.2 Reqrement Gathering | bar: week 1
1.3 Interview with the clent and staff | bar: week 1
1.4 Requirement Analysis | bar: week 1
1.5 Specifying Key Features | bar: week 1
2. Project Proposal | bar: week 2
2.1 Creating project proposal | bar: week 2
2.2 Showing to the supervisor | bar: week 2
2.3 Submssion | bar: week 2
3.Getting Approval | bar: week 3
4.Software Requirement Specification | bar: week 4
5. Design system architecture | bar: week 4 to week 9
5.1 Desgning system | bar: week 4 to week 8
5.2 Design approval | bar: week 6 to week 9
6. Implementation | bar: week 10 to week 22
6.1 User Interface Design | bar: week 10 to week 19
6.2 Creating Database | bar: week 10 to week 19
6.3 Designing Backend | bar: week 10 to week 19
6.4 Coding | bar: week 11 to week 22
6.5 Connecting the Database | bar: week 20 to week 22
7. Software Evaluation & Testing | bar: week 22 to week 25
8. Creating final report | bar: week 26 to week 27
8.1 Creating final presentation | bar: week 26 to week 27
9. Final Product Demonstration | bar: week 28 to week 29
10. Submission of final report and final viva | bar: week 30